## Project Status
# | Module / Feature | Sub-Feature | Status | Priority | Notes
CORE INTERVIEW ENGINE
1 | Resume Parsing | PDF/DOCX upload & extraction | Done | P0 | pdfplumber + docx2txt
2 | Resume Parsing | Candidate profiling (domain, level, skills) | Done | P0 | Auto-detects from resume
3 | Question Generation | LLM-powered adaptive questions | Done | P0 | Uses conversation history
4 | Question Generation | Follow-up question logic | Done | P0 | Based on answer quality
5 | Question Generation | Contradiction pairs testing | Done | P1 | 3 pairs per domain/level
6 | Answer Processing | Real-time STT transcription | Done | P0 | OpenAI Whisper, Deepgram, Inworld
7 | Answer Processing | TTS response synthesis | Done | P0 | Deepgram Aura, Inworld, OpenAI, Kugel
8 | Evaluation | Per-question scoring | Done | P0 | Structured rubric per level
9 | Evaluation | Overall session evaluation | Done | P0 | Score, grade, trajectory, recommendation
10 | Evaluation | Behavioral analysis | Done | P1 | Filler words, pauses, pronouns
11 | Session Management | In-memory + PostgreSQL state | Done | P0 | Dual-layer with Redis cache
12 | Session Management | Cross-worker session sharing | Done | P0 | DB-backed sync
13 | WebSocket Audio | Real-time audio streaming | Done | P0 | Browser VAD + server processing
DOMAINS & EXPERIENCE LEVELS
14 | Domain: Physical Design | Interview prompts | Done | P0 | experienced_junior + experienced_senior
15 | Domain: Analog Layout | Interview prompts | Done | P0 | experienced_junior + experienced_senior
16 | Domain: Design Verification | Interview prompts | Done | P0 | experienced_junior + experienced_senior
17 | Domain: Physical Design | Eval prompts | Done | P0 | experienced_junior + experienced_senior
18 | Domain: Analog Layout | Eval prompts | Done | P0 | experienced_junior + experienced_senior
19 | Domain: Design Verification | Eval prompts | Done | P0 | experienced_junior + experienced_senior
20 | Level: fresh_graduate | Interview + eval prompts | Pending | P1 | No prompts exist yet
21 | Level: trained_fresher | Interview + eval prompts | Pending | P1 | Backup files exist (.bak) but not active
22 | STT Domain Hints | Per-domain transcription prompts | Done | P1 | 3 domain-specific hint files
ANTI-CHEAT & PROCTORING
23 | Gaze Tracking | ML ensemble classifier | Done | P1 | sklearn model (gaze_ensemble_model.pkl)
24 | Face Verification | AWS Rekognition face compare | Done | P1 | Register + compare + liveness
25 | Face Verification | Glasses detection | Done | P2 | AWS Rekognition
26 | Speaker Verification | Resemblyzer voice matching | Done | P1 | 256-dim embeddings, threshold 0.75
27 | Speaker Verification | ECAPA-TDNN model integration | Pending | P2 | Model downloaded at models/spkrec-ecapa/ but NOT integrated
28 | Speaker Verification | Mismatch counting (no interview end) | Done | P1 | Counts mismatches, reports in callback
29 | Tab Switch Detection | Browser tab change logging | Done | P1 | Logged in anticheat_log
30 | AI Detection | AI-generated answer flagging | Done | P2 | Flags in anticheat_log
31 | Keystroke Monitoring | Copy-paste & keystroke events | Done | P2 | Behavioral event logging
LMS INTEGRATION
32 | LMS Launch | POST /api/lms/launch endpoint | Done | P0 | SAML/OAuth, resume upload, redirect
33 | LMS Callback | POST results to callback_url | Done | P0 | Structured payload with Q&A, retry logic
34 | LMS Callback | Student + result + questions + integrity | Done | P0 | Full transcript included
35 | LMS Callback | Staging endpoint tested | Done | P1 | http://13.232.251.185 — 200 OK
36 | LMS Callback | Production endpoint | Pending | P0 | eduspark.sumedhait.com returns 404 — LMS team needs to deploy
37 | LMS Integration Guide | Documentation for LMS team | Done | P1 | LMS_INTEGRATION_GUIDE.md
38 | LMS Test Page | lms_test.html testing UI | Done | P2 | SAML/OAuth launch simulation
ADMIN DASHBOARD
39 | Session Browser | List/filter/view sessions | Done | P0 | With search, date range, domain filter
40 | LLM Config | Model switcher (17 models) | Done | P0 | qgen + eval model selection
41 | Voice Config | TTS/STT provider switcher | Done | P1 | 4 TTS + 3 STT providers
42 | Prompt Editor | Edit eval prompts in-browser | Done | P1 | Save/reset per level
43 | Expert Reviews | Submit human expert scores | Done | P1 | Real INSERT + auto AI score lookup
44 | Share Links | Public session review URLs | Done | P2 | Token-based, no auth required
45 | Rerun Evaluation | Re-evaluate ended sessions | Done | P1 | POST /api/admin/rerun-eval/{sid}
46 | Prompt Playground | Test eval prompts live | Done | P2 | POST /api/admin/prompt-playground
47 | Anticheat Config | Configure thresholds | Done | P2 | GET/POST /api/admin/anticheat-config
COGNITION AI (SELF-IMPROVING ENGINE)
48 | Signal Collectors | eval_parse_fail detector | Done | P1 | Detects evaluation parse errors
49 | Signal Collectors | difficulty_ramp detector | Done | P1 | Score drop >20% mid-interview
50 | Signal Collectors | topic_gap detector | Done | P1 | Resume skills never asked about
51 | Signal Collectors | cost_anomaly detector | Done | P1 | Token usage >2σ from mean
52 | Signal Collectors | followup_quality detector | Done | P1 | Follow-ups scoring 25%+ lower
53 | Signal Collectors | score_drift detector | Done | P1 | Expert vs AI disagreement >1.5
54 | Diagnosis Engine | LLM-powered prompt fix suggestions | Done | P1 | Auto-triggers at 3+ signals, 24h cooldown
55 | Background Sweeper | 600s interval incremental scan | Done | P1 | Watermark-based, daemon thread
56 | Admin Endpoints | Signals/summary/diagnoses/trigger | Done | P1 | 5 endpoints under /api/admin/cognition/
57 | Cognition Model Config | Separate cognition_model in RUNTIME_CONFIG | Done | P2 | us.anthropic.claude-haiku
58 | Auto-Apply Fixes | Apply diagnosis suggestions to prompts | Pending | P2 | Manual review only — no auto-patching yet
COST & OBSERVABILITY
59 | LLM Cost Tracking | Per-call token + cost logging | Done | P1 | 17-model pricing matrix
60 | Observability Dashboard | Summary + log query endpoints | Done | P1 | /api/observability/summary + /logs
61 | Load Testing | loadtest.py (4 scenarios) | Done | P2 | health, session, turn, stream
INFRASTRUCTURE & DEPLOYMENT
62 | PostgreSQL | Schema migration (15 tables) | Done | P0 | Auto-creates on startup
63 | Redis Cache | Session caching (2h TTL) | Done | P1 | Optional — works without Redis
64 | AWS Bedrock | Claude model access | Done | P0 | Primary LLM provider
65 | AWS Rekognition | Face verification | Done | P1 | Register, compare, liveness
66 | Secrets Management | Env vars + AWS SSM + Secrets Manager | Done | P1 | secrets_proxy.py
67 | EC2 Deployment | nginx + uvicorn on port 8001 | Done | P0 | Deploy via git pull
68 | EC2 Server | Pull latest code changes | Pending | P0 | Server running OLD code — needs git pull + restart
69 | SSL/HTTPS | Production HTTPS | Partial | P0 | nginx handles SSL but cert status unknown
70 | CI/CD Pipeline | Automated testing & deploy | Pending | P2 | Manual git pull deploy currently
71 | Docker | Containerized deployment | Pending | P3 | Not containerized
72 | Monitoring & Alerts | Production health monitoring | Pending | P2 | No alerting system in place
73 | Logging | Centralized log aggregation | Pending | P2 | Console logging only, no log aggregation
TESTING
74 | Unit Tests | Python unit test suite | Pending | P2 | No test files exist
75 | Integration Tests | API endpoint tests | Pending | P2 | No automated API tests
76 | Load Tests | Performance benchmarking | Done | P2 | loadtest.py covers 4 scenarios
77 | Speaker Test Page | Audio device test UI | Done | P2 | speaker_test.html
PENDING / FUTURE WORK
78 | Voice Cloning | Clone interviewer voice | Pending | P3 | Placeholder endpoint exists, not implemented
79 | Multi-Language Support | Non-English interviews | Pending | P3 | English only currently
80 | Candidate Portal | Student dashboard for past results | Pending | P3 | No student-facing dashboard
81 | Analytics Dashboard | Interview analytics & trends | Pending | P2 | Admin sees sessions but no trend charts
82 | Email Notifications | Send results to candidates | Pending | P3 | No email integration
83 | Batch Interview | Schedule/queue multiple interviews | Pending | P3 | One at a time currently
84 | Mobile Responsive | Mobile-optimized interview UI | Pending | P3 | Desktop-focused layout
85 | Rate Limiting | API rate limiting | Pending | P2 | No rate limits on endpoints

## Summary
PROJECT STATUS SUMMARY
Metric | Count | Percentage
Total Features | 85 | 100%
Completed (Done) | 64 | 75%
Partially Done | 1 | 1%
Pending | 20 | 23%
P0 (Critical) | 28
P0 Done | 25
P0 Pending | 3
P1 (Important) | 30
P1 Done | 28
P1 Pending | 2
Total API Endpoints | 55+
Database Tables | 15
LLM Models Supported | 17
TTS Providers | 4
STT Providers | 3
Domains | 3
Experience Levels (active) | 2 of 4
Scored Sessions (Production) | 12

## API Endpoints
# | Method | Endpoint | Category | Purpose | Auth Required
1 | POST | /api/login | Auth | Admin login | No
2 | POST | /api/auth/login | Auth | Auth login | No
3 | POST | /api/auth/logout | Auth | Logout | Yes
4 | GET | /api/auth/me | Auth | Current user profile | Yes
5 | POST | /api/create-session | Session | Create interview session | No
6 | GET | /api/get-session | Session | Fetch session state | No
7 | POST | /api/start-interview | Session | Start interview + gen first Q | No
8 | POST | /api/submit-answer | Session | Submit answer (blocking) | No
9 | POST | /api/stream-answer | Session | Stream answer (SSE) | No
10 | POST | /api/end-session | Session | End session + auto-eval | No
11 | POST | /api/generate-report | Session | Generate eval report | No
12 | POST | /api/transcribe | Speech | STT transcription | No
13 | WS | /ws/audio | Speech | WebSocket audio streaming | No
14 | POST | /api/toggle-tts | Speech | Enable/disable TTS | No
15 | POST | /api/parse-resume | Resume | Parse PDF/DOCX resume | No
16 | POST | /api/lms/launch | LMS | Launch from LMS (SAML/OAuth) | API Key
17 | POST | /api/anticheat-event | Anti-Cheat | Log behavioral event | No
18 | GET | /api/anticheat-settings | Anti-Cheat | Get anticheat config | No
19 | POST | /api/anticheat/gaze | Anti-Cheat | Submit gaze tracking data | No
20 | GET | /api/face/check | Face | Check face reference exists | No
21 | POST | /api/face/register | Face | Register face reference | No
22 | POST | /api/face/detect-glasses | Face | Detect glasses | No
23 | POST | /api/face/compare | Face | Compare face to reference | No
24 | GET | /api/admin/llm-config | Admin-LLM | Get model config | Yes
25 | POST | /api/admin/llm-config | Admin-LLM | Switch models | Yes
26 | GET | /api/admin/llm-prompts | Admin-LLM | Get eval prompts | Yes
27 | POST | /api/admin/llm-prompts | Admin-LLM | Save/reset eval prompts | Yes
28 | GET | /api/admin/qgen-prompt | Admin-LLM | Preview qgen prompt | Yes
29 | GET | /api/admin/interview-prompt | Admin-LLM | Preview interviewer prompt | Yes
30 | GET | /api/tts-status | Admin-Voice | Check TTS status | No
31 | GET | /api/admin/stt-config | Admin-Voice | Get STT config | Yes
32 | POST | /api/admin/stt-config | Admin-Voice | Change STT provider | Yes
33 | POST | /api/admin/stt-test | Admin-Voice | Test STT with audio | Yes
34 | GET | /api/admin/voice-library | Admin-Voice | List TTS voices | Yes
35 | POST | /api/admin/test-tts | Admin-Voice | Test TTS synthesis | Yes
36 | POST | /api/admin/set-interview-voice | Admin-Voice | Set interviewer voice | Yes
37 | POST | /api/playground/tts | Admin-Voice | TTS playground | Yes
38 | GET | /api/admin/sessions | Admin-Sessions | List all sessions | Yes
39 | GET | /api/admin/session/{sid} | Admin-Sessions | Session detail | Yes
40 | POST | /api/admin/rerun-eval/{sid} | Admin-Sessions | Rerun evaluation | Yes
41 | POST | /api/admin/share-link | Admin-Sessions | Generate share link | Yes
42 | GET | /api/shared/session/{token} | Public | Shared session review | No
43 | GET | /api/admin/anticheat-config | Admin-Anticheat | Get anticheat thresholds | Yes
44 | POST | /api/admin/anticheat-config | Admin-Anticheat | Update anticheat config | Yes
45 | POST | /api/admin/review | Admin-Review | Submit expert review | Yes
46 | GET | /api/admin/reviews | Admin-Review | List all reviews | Yes
47 | GET | /api/admin/reviews/{sid} | Admin-Review | Reviews per session | Yes
48 | GET | /api/admin/cognition/signals | Cognition | List signals | Yes
49 | GET | /api/admin/cognition/summary | Cognition | Dashboard summary | Yes
50 | GET | /api/admin/cognition/diagnoses | Cognition | List diagnoses | Yes
51 | POST | /api/admin/cognition/diagnoses/{id} | Cognition | Update diagnosis status | Yes
52 | POST | /api/admin/cognition/trigger | Cognition | Manual sweep trigger | Yes
53 | POST | /api/admin/prompt-playground | Admin-Playground | Test eval prompt live | Yes
54 | GET | /health | System | Health check | No
55 | GET | /api/lobby-config | System | Available domains + levels | No
56 | GET | /api/domains | System | Supported domains | No
57 | GET | /api/observability/summary | Observability | Cost/token summary | Yes
58 | GET | /api/observability/logs | Observability | LLM call history | Yes

## Database Schema
# | Table Name | Purpose | Key Columns | Status
1 | active_sessions | Live session state (primary) | session_id (TEXT PK), session_data (JSONB) | Active
2 | candidate_history | Email-indexed session history | email, session_id, session_summary (JSONB) | Active
3 | app_config | Shared runtime config | key (TEXT PK), value (JSONB) | Active
4 | face_references | Face encodings for verification | email (PK), face_encoding, liveness_confidence | Active
5 | cognition_signals | Detected prompt quality issues | signal_type, severity, domain, evidence (JSONB) | Active
6 | cognition_diagnoses | LLM prompt fix suggestions | domain, level, problem, suggestion, status | Active
7 | cognition_state | Sweep watermarks | state_key (TEXT PK), state_value (JSONB) | Active
8 | expert_reviews | Human expert scores | session_id, reviewer_name, score, ai_score, delta | Active
9 | llm_calls | LLM cost tracking | step, model, tokens, latency, cost_usd | Active
10 | candidates | Candidate profiles | name, domain, level, skills, tools | Legacy
11 | sessions | Normalized sessions | mode, domain, level, score, grade | Legacy (unused)
12 | turns | Q&A exchanges | question, answer, duration, difficulty | Legacy
13 | evaluations | Per-turn scores | score, quality, accuracy, expected_points | Legacy
14 | behavioral_signals | Speech metrics | filler_rate, pronoun_rate, pause_duration | Legacy
15 | reports | Session summaries | technical/theory/communication scores | Legacy

## Action Items
# | Action Item | Category | Priority | Effort | Details
1 | EC2: git pull + restart | Deployment | P0 | 15 min | Server running old code. Cognition AI, speaker mismatch counting, enhanced LMS callback not deployed yet
2 | Production callback endpoint | LMS | P0 | LMS team | eduspark.sumedhait.com/api/interview-result returns 404. LMS team needs to deploy their callback route
3 | fresh_graduate prompts | Content | P1 | 2-3 hours | Create interview + eval prompts for fresh_graduate level (all 3 domains)
4 | trained_fresher prompts | Content | P1 | 2-3 hours | Restore/create interview + eval prompts for trained_fresher level (backup files exist)
5 | ECAPA-TDNN speaker verification | Anti-Cheat | P2 | 4-6 hours | Integrate SpeechBrain ECAPA-TDNN model (192-dim, better accuracy) to replace Resemblyzer
6 | Cognition auto-apply fixes | Cognition AI | P2 | 3-4 hours | Currently diagnosis suggestions are manual. Auto-apply with human approval workflow
7 | Unit test suite | Testing | P2 | 1-2 days | No test files exist. Add pytest tests for database.py, cognition.py, core endpoints
8 | API integration tests | Testing | P2 | 1 day | Automated endpoint tests with test DB
9 | Rate limiting | Security | P2 | 2-3 hours | No rate limits on any endpoint. Add per-IP limits on auth, session creation
10 | Monitoring & alerts | Infrastructure | P2 | 4-6 hours | No health monitoring or alerting. Add uptime checks, error rate alerts
11 | Log aggregation | Infrastructure | P2 | 3-4 hours | Console logging only. Set up CloudWatch or similar
12 | SSL cert verification | Infrastructure | P1 | 30 min | Verify SSL cert status and auto-renewal on production
13 | Analytics dashboard | Admin | P2 | 1-2 days | Interview trends, score distribution, domain breakdown charts
14 | Voice cloning | Speech | P3 | 1-2 days | Placeholder endpoint exists but not implemented
15 | CI/CD pipeline | DevOps | P2 | 1 day | Currently manual git pull. Set up GitHub Actions or similar
16 | Docker containerization | DevOps | P3 | 4-6 hours | Not containerized. Add Dockerfile + docker-compose
17 | Mobile responsive UI | Frontend | P3 | 2-3 days | Desktop-focused layout, needs mobile optimization
18 | Candidate portal | Frontend | P3 | 2-3 days | No student-facing dashboard for past results
19 | Email notifications | Integration | P3 | 4-6 hours | Send interview results to candidates via email